## Task_Table
PLANNING
| Name | Days | Weight | [31 empty] | April | [29 empty] | Mei | [30 empty] | JUN
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Termin 1 30 % | SIGMA Implementation Task | 115 | 100
| Fase 1 |  | 30
| Project Preparation | 2 | 1
| Kick Off | 2 | 1 | bar: 3
| Requirement Preparation | 14 | 29
| Gap Analysis | 5 | 6 | bar: 5 to 7; 12 to 14
| Blue Print | 9 | 6 | bar: 17 to 19; 24 to 26
| Mockup | 9 | 17 | bar: 4 to 7; 10 to 14; 17 to 21; 24 to 26
Termin 2 65 % | Fase 2 |  | 65
| Enhanchement | 22 | 49
| Environment Preparation | 2 | 1 | bar: 7
| Development | 15 | 45 | 27: 1; 28: 1; April 8: 1; April 9: 1; April 10: 1; April 11: 1; April 14: 1; April 15: 1; April 16: 1; April 17: 1; April 18: 1; April 21: 1; April 22: 1; April 23: 1; April 24: 1; April 25: 1; April 28: 1; April 29: 1; April 30: 1; Mei 1: 1; Mei 2: 1; Mei 5: 1; Mei 6: 1; Mei 7: 1; Mei 8: 1; Mei 9: 1; Mei 12: 1; Mei 13: 1; Mei 14: 1; Mei 15: 1; Mei 16: 1; Mei 19: 1; Mei 20: 1; Mei 21: 1; Mei 22: 1; Mei 23: 1; Mei 26: 1; Mei 27: 1; Mei 28: 1; Mei 29: 1; Mei 30: 1; JUN 2: 1; JUN 3: 1; JUN 4: 1; JUN 5: 0.5; JUN 6: 0.5
| Unit Testing | 5 | 3 | bar: JUN 9 to JUN 11
| Acceptance | 10 | 16
| SIT | 3 | 3 | bar: JUN 11 to JUN 13
| UAT | 4 | 10 | JUN 16: 2; JUN 17: 2; JUN 18: 2; JUN 19: 2; JUN 20: 2
| EUT | 3 | 3 | JUN 23: 2; JUN 24: 1
Termin 3 5 % | Fase 3 |  | 5
| Support | 60 | 5
| Support | 60 | 5 | JUN 25: 1; JUN 26: 1; JUN 27: 1; JUN 30: 2
| Total | 108 | 100 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 2
| Accumulated |  |  | 0 | 0 | 1 | 2 | 4 | 6 | 9 | 9 | 9 | 10 | 11 | 13 | 15 | 17 | 17 | 17 | 19 | 21 | 23 | 24 | 25 | 25 | 25 | 27 | 29 | 31 | 32 | 33 | 33 | 33 |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 35 | 36 | 37 | 37 | 37 | 38 | 39 | 40 | 41 | 42 | 42 | 42 | 43 | 44 | 45 | 46 | 47 | 47 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 58 | 59 | 60 | 61 | 62 | 62 | 62 | 63 | 64 | 65 | 66 | 67 | 67 | 67 | 68 | 69 | 70 | 71 | 72 | 72 | 72 | 73 | 74 | 75 | 75.5 | 76 | 76 | 76 | 77 | 78 | 80 | 81 | 82 | 82 | 82 | 84 | 86 | 88 | 90 | 92 | 92 | 92 | 94 | 95 | 96 | 97 | 98 | 98 | 98 | 100
REAL
| Name | Planning | Real | April 1: April; Mei 1: Mei; JUN 1: JUN
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Termin 1 30 % | SIGMA Implementation Task | 100 | 100
| Fase 1 | 30 | 8.3
| Project Preparation | 1 | 1
| Kick Off | 1 | 1 | bar: 3
| Requirement Preparation | 29 | 7.3
| Gap Analysis | 6 | 3.5 | 3: 1; 4: 1; 5: 0.5; 6: 0.5; 7: 0.5
| Blue Print | 6 | 1.9 | 3: 0.2; 4: 0.2; 5: 0.5; 6: 0.5; 7: 0.5
| Mockup | 17 | 1.9 | 3: 0.2; 4: 0.2; 5: 0.5; 6: 0.5; 7: 0.5
Termin 2 65 % | Fase 2 | 65 | 0
| Enhanchement | 49 | 0
| Environment Preparation | 1 | 0
| Development | 45 | 0
| Unit Testing | 3 | 0
| Acceptance | 16 | 0
| SIT | 3 | 0
| UAT | 10 | 0
| EUT | 3 | 0
Termin 3 5 % | Fase 3 | 5 | 0
| Support | 5 | 0
| Support | 5 | 0
| Total | 100 | 8.3 | 0 | 0 | 2.4 | 1.4 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulated |  |  | 0 | 0 | 2.4 | 3.8 | 5.3 | 6.8 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 |  | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3
| Planning |  |  | 0 | 0 | 1 | 2 | 4 | 6 | 9 | 9 | 9 | 10 | 11 | 13 | 15 | 17 | 17 | 17 | 19 | 21 | 23 | 24 | 25 | 25 | 25 | 27 | 29 | 31 | 32 | 33 | 33 | 33 |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 35 | 36 | 37 | 37 | 37 | 38 | 39 | 40 | 41 | 42 | 42 | 42 | 43 | 44 | 45 | 46 | 47 | 47 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 58 | 59 | 60 | 61 | 62 | 62 | 62 | 63 | 64 | 65 | 66 | 67 | 67 | 67 | 68 | 69 | 70 | 71 | 72 | 72 | 72 | 73 | 74 | 75 | 75.5 | 76 | 76 | 76 | 77 | 78 | 80 | 81 | 82 | 82 | 82 | 84 | 86 | 88 | 90 | 92 | 92 | 92 | 94 | 95 | 96 | 97 | 98 | 98 | 98 | 100
| Gap |  |  | 0 | 0 | -1.4 | -1.8 | -1.3 | -0.8 | 0.7 | 0.7 | 0.7 | 1.7 | 2.7 | 4.7 | 6.7 | 8.7 | 8.7 | 8.7 | 10.7 | 12.7 | 14.7 | 15.7 | 16.7 | 16.7 | 16.7 | 18.7 | 20.7 | 22.7 | 23.7 | 24.7 | 24.7 | 24.7 | 0 | 24.7 | 24.7 | 24.7 | 24.7 | 24.7 | 24.7 | 24.7 | 25.7 | 26.7 | 27.7 | 28.7 | 28.7 | 28.7 | 29.7 | 30.7 | 31.7 | 32.7 | 33.7 | 33.7 | 33.7 | 34.7 | 35.7 | 36.7 | 37.7 | 38.7 | 38.7 | 38.7 | 39.7 | 40.7 | 41.7 | 42.7 | 43.7 | 43.7 | 43.7 | 44.7 | 45.7 | 46.7 | 47.7 | 48.7 | 48.7 | 48.7 | 49.7 | 50.7 | 51.7 | 52.7 | 53.7 | 53.7 | 53.7 | 54.7 | 55.7 | 56.7 | 57.7 | 58.7 | 58.7 | 58.7 | 59.7 | 60.7 | 61.7 | 62.7 | 63.7 | 63.7 | 63.7 | 64.7 | 65.7 | 66.7 | 67.2 | 67.7 | 67.7 | 67.7 | 68.7 | 69.7 | 71.7 | 72.7 | 73.7 | 73.7 | 73.7 | 75.7 | 77.7 | 79.7 | 81.7 | 83.7 | 83.7 | 83.7 | 85.7 | 86.7 | 87.7 | 88.7 | 89.7 | 89.7 | 89.7 | 91.7
0.6

## Copy of Task_Table
PLANNING
| Name | Days | Weight | Maret | [30 empty] | April | [29 empty] | Mei | [30 empty] | JUN | [29 empty] | JUL | [30 empty] | AGUSTUS | [30 empty] | SEPTEMBER
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Termin 1 30 % | MD ROYALTY Implementation Task | 115 | 100
| TERMIN 1 |  | 30
| Project Preparation | 4 | 5
| Kick Off | 2 | 2 | bar: Maret 1; Maret 6
| Project Charter | 2 | 3 | bar: Maret 6; Maret 8; Maret 15
| Requirement Preparation | 14 | 25
| Gap Analysis | 5 | 10 | bar: Maret 7 to Maret 8; Maret 13 to Maret 15; Maret 18 to Maret 22
| Blue Print | 9 | 15 | Maret 18: 1; Maret 19: 1; Maret 20: 1; Maret 21: 1; Maret 22: 1; Maret 25: 2; Maret 26: 2; Maret 27: 2; Maret 28: 2; Maret 29: 2
Termin 2 65 % | Termin 2 |  | 69
| Enhanchement | 22 | 33
| Environment Preparation | 2 | 2 | bar: Maret 8; Maret 15
| Development | 15 | 26 | bar: Maret 18 to Maret 22; Maret 25 to Maret 29; April 1 to April 5; April 15 to April 19; April 22 to April 26; April 29
| Unit Testing | 5 | 5 | bar: April 29 to Mei 1; Mei 27 to Mei 28
| Acceptance | 10 | 20
| SIT | 3 | 5 | Mei 6: 1; Mei 7: 1; Mei 8: 1; JUN 7: 2
| UAT | 4 | 10 | Mei 13: 2; Mei 14: 2; Mei 15: 1; Mei 16: 1; Mei 17: 1; Mei 20: 1; JUN 24: 1; JUN 25: 1
| EUT | 3 | 5 | JUN 7: 3; JUL 11: 1; JUL 15: 1
| Live Preparation | 7 | 13
| Migration Data Preparation | 3 | 8 | bar: JUN 17 to JUN 21; JUN 24 to JUN 25; JUL 8
| Upload Migration to Production | 2 | 5 | bar: JUN 26; JUL 2; JUL 31; AGUSTUS 7; AGUSTUS 14
| Transport Production |  | 2 | bar: JUL 24; AGUSTUS 19
| Golive | 2 | 1 | bar: SEPTEMBER 1
Termin 3 5 % | Termin 3 |  | 1
| Support | 60 | 1
| Support | 60 | 1 | bar: SEPTEMBER 2
| Total | 117 | 100 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulated |  |  | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 8 | 9 | 12 | 12 | 12 | 15 | 18 | 21 | 24 | 27 | 27 | 27 | 30 | 33 | 36 | 39 | 42 | 42 | 42 | 43 | 44 | 45 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 59 | 60 | 61 | 61 | 61 | 61 | 61 | 62 | 63 | 64 | 64 | 64 | 64 | 64 | 66 | 68 | 69 | 70 | 71 | 71 | 71 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 73 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 80 | 81 | 82 | 83 | 84 | 84 | 84 | 86 | 88 | 89 | 89 | 89 | 89 | 89 | 89 | 90 | 90 | 90 | 90 | 90 | 90 | 91 | 91 | 91 | 92 | 92 | 92 | 92 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 97 | 97 | 97 | 97 | 97 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
ACTUAL
| Name | Planning | Actual | Maret 1: Maret; April 1: April; Mei 1: Mei; JUN 1: JUN; JUL 1: JUL; AGUSTUS 1: AGUSTUS; SEPTEMBER 1: SEPTEMBER
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 27 | 28 | 5 | 6 | 7 | 8 | 9 | 27 | 28 | 12 | 13 | 14 | 15 | 16 | 27 | 28 | 19 | 20 | 21 | 22 | 23 | 27 | 28 | 26 | 27 | 28 | 29 | 30 | 27 | 28 | 2 | 3 | 4 | 5 | 6 | 27 | 28 | 9 | 10 | 11 | 12 | 13 | 27 | 28 | 16 | 17 | 18 | 19 | 20 | 27 | 28 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 30
Termin 1 30 % | MD ROYALTY Implementation Task | 100 | 100
| Termin 1 | 30 | 30
| Project Preparation | 5 | 5
| Kick Off | 2 | 2 | bar: Maret 1; Maret 6
| Project Charter | 3 | 3 | Maret 8: 1; Maret 12: 0.5; Maret 20: 1; Maret 25: 0.5
| Requirement Preparation | 25 | 25
| Gap Analysis | 10 | 10 | Maret 7: 0.5; Maret 8: 1; Maret 13: 0.5; Maret 14: 0.5; Maret 15: 0.5; Maret 18: 1; Maret 19: 1; Maret 20: 1; Maret 21: 0.5; Maret 22: 1; Maret 25: 1; Maret 26: 1; Maret 27: 0.5
| Blue Print | 15 | 15 | Maret 18: 0.5; Maret 19: 0.5; Maret 20: 0.5; Maret 21: 0.5; Maret 22: 0.5; Maret 25: 0.5; Maret 26: 1; Maret 27: 1; Maret 28: 1; Maret 29: 1; April 1: 2; April 2: 1; April 3: 1; April 4: 1; April 15: 0.5; April 17: 0.5; April 22: 0.5; April 23: 0.5; Mei 13: 0.5; Mei 20: 0.5
| Termin 2 | 69 | 69
Termin 2 65 % | Enhanchement | 33 | 33
| Environment Preparation | 2 | 2 | Maret 15: 0.5; Maret 20: 0.5; Maret 25: 1
| Development | 26 | 26 | Maret 18: 1; Maret 19: 1; Maret 20: 1; Maret 21: 0.5; Maret 22: 0.5; Maret 25: 0.5; Maret 26: 0.5; Maret 27: 0.5; Maret 28: 0.5; Maret 29: 0.5; April 1: 0.5; April 2: 0.5; April 3: 0.5; April 4: 0.5; April 5: 0.5; April 15: 0.5; April 16: 0.5; April 17: 0.5; April 18: 0.5; April 22: 0.5; April 23: 0.5; April 24: 0.5; April 25: 0.5; April 26: 0.5; April 29: 0.5; April 30: 0.5; Mei 1: 0.5; Mei 2: 0.5; Mei 3: 0.5; Mei 6: 0.5; Mei 7: 0.5; Mei 8: 0.2; Mei 9: 0.2; Mei 10: 0.2; Mei 13: 0.5; Mei 14: 0.6; Mei 15: 1; Mei 16: 1; Mei 17: 1; Mei 20: 0.5; Mei 21: 0,2; Mei 22: 0.5; Mei 23: 0.2; Mei 24: 0.2; Mei 27: 0.2; Mei 28: 0.2; Mei 29: 0.2; JUN 5: 0.5; JUN 6: 0.5; JUN 11: 0.5; JUN 12: 0.5; JUN 13: 0.1; JUN 17: 0.1; JUN 18: 0.1
| Unit Testing | 5 | 5 | bar: April 29 to Mei 1; Mei 27 to Mei 28
| Acceptance | 20 | 20
| SIT | 5 | 5 | bar: Mei 7 to Mei 9; JUN 14; JUN 19
| UAT | 10 | 10 | Mei 7: 1; Mei 8: 1; Mei 9: 1; Mei 10: 1; Mei 13: 2; Mei 14: 1; Mei 20: 0,5; Mei 21: 1; JUL 2: 0.5; JUL 3: 0.5; JUL 4: 0.5; JUL 5: 0.2; JUL 8: 0.3
| EUT | 5 | 5 | JUN 7: 3; JUL 16: 1; JUL 17: 1
| Live Preparation | 13 | 13
| Preparation Master Data | 8 | 8 | Mei 29: 0.1; Mei 30: 0.1; Mei 31: 0.1; JUN 3: 0.1; JUN 4: 0.1; JUN 5: 0.1; JUN 6: 0.1; JUN 7: 0.1; JUN 10: 0.1; JUN 11: 0.1; JUN 12: 0.1; JUN 13: 0.1; JUN 14: 0.1; JUN 18: 0.1; JUN 19: 0.1; JUN 20: 0.1; JUN 21: 0.1; JUN 24: 0.2; JUN 25: 0.2; JUN 26: 0.2; JUN 27: 0.2; JUN 28: 0.2; JUL 1: 0.2; JUL 2: 0.2; JUL 3: 0.2; JUL 4: 0.2; JUL 5: 0.2; JUL 8: 0.2; JUL 9: 0.2; JUL 10: 0.2; JUL 11: 0.2; JUL 12: 0.2; JUL 15: 0.2; JUL 16: 0.2; JUL 17: 0.1; JUL 18: 0.3; JUL 19: 0.1; JUL 22: 0.1; JUL 23: 0.1; JUL 24: 0.1; JUL 25: 0.1; JUL 26: 0.1; JUL 29: 0.1; JUL 30: 0.1; JUL 31: 0.1; AGUSTUS 1: 0.1; AGUSTUS 2: 0.1; AGUSTUS 5: 0.2; AGUSTUS 6: 0.1; AGUSTUS 7: 0.1; AGUSTUS 12: 0.1; AGUSTUS 13: 0.1; AGUSTUS 14: 0.1; AGUSTUS 15: 0.1; AGUSTUS 16: 0.1; AGUSTUS 19: 0.2; AGUSTUS 20: 0.1; AGUSTUS 21: 0.2
| Upload Migration to Production | 5 | 5 | JUN 28: 0.2; JUL 5: 0.4; JUL 15: 0.2; JUL 16: 0.2; JUL 25: 0.2; JUL 26: 0.2; JUL 29: 0.2; JUL 30: 0.2; JUL 31: 0.2; AGUSTUS 5: 0.1; AGUSTUS 6: 0.1; AGUSTUS 7: 0.1; AGUSTUS 12: 1; AGUSTUS 13: 0.3; AGUSTUS 14: 0.4; AGUSTUS 19: 0.2; AGUSTUS 20: 0.2; AGUSTUS 21: 0.1; AGUSTUS 26: 0.1; AGUSTUS 27: 0.3; AGUSTUS 28: 0.1
| Transport Production | 2 | 2 | JUL 23: 0.5; JUL 26: 0.5; AGUSTUS 29: 0.5; AGUSTUS 30: 0.5
| Golive | 1 | 1 | bar: SEPTEMBER 28
| Termin 3 | 1 | 0
Termin 3 5 % | Support | 1 | 0
| Support | 1 | 0
| Total | 100 | 99 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 2 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 0 | 0 | 2.5 | 2.5 | 4 | 1.5 | 2 | 0 | 0 | 3.5 | 2.5 | 2 | 1.5 | 1.5 | 0 | 0 | 2.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 2.5 | 2.2 | 2.2 | 1.2 | 0 | 0 | 3 | 1.6 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 1.2 | 1.2 | 0.3 | 0.1 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0.6 | 0.6 | 3.1 | 0 | 0 | 0.1 | 0.6 | 0.6 | 0.2 | 1.1 | 0 | 0 | 0.1 | 0.2 | 1.1 | 0.1 | 0.1 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0 | 0 | 0.2 | 0.7 | 0.7 | 0.7 | 0.8 | 0 | 0 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0.4 | 1.4 | 1.1 | 0.3 | 0.1 | 0 | 0 | 0.1 | 0.6 | 0.1 | 0.3 | 0.8 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0 | 0 | 0.3 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 1.1 | 0.4 | 0.5 | 0.1 | 0.1 | 0 | 0 | 0.4 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0.1 | 0.3 | 0.1 | 0.5 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulated |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 4.5 | 4.5 | 4.5 | 4.5 | 5 | 5.5 | 6 | 7 | 7 | 7 | 9.5 | 12 | 16 | 17.5 | 19.5 | 19.5 | 19.5 | 23 | 25.5 | 27.5 | 29 | 30.5 | 30.5 | 30.5 | 33 | 34.5 | 36 | 37.5 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39.5 | 40.5 | 41 | 41 | 41 | 41 | 42 | 43 | 43.5 | 44 | 44.5 | 44.5 | 44.5 | 46 | 47.5 | 49 | 49.5 | 50 | 50 | 50 | 50.5 | 53 | 55.2 | 57.4 | 58.6 | 58.6 | 58.6 | 61.6 | 63.2 | 64.2 | 65.2 | 66.2 | 66.2 | 66.2 | 67.2 | 68.2 | 68.7 | 68.9 | 69.1 | 69.1 | 69.1 | 70.3 | 71.5 | 71.8 | 71.9 | 72 | 72 | 72 | 72.1 | 72.2 | 72.8 | 73.4 | 76.5 | 76.5 | 76.5 | 76.6 | 77.2 | 77.8 | 78 | 79.1 | 79.1 | 79.1 | 79.2 | 79.4 | 80.5 | 80.6 | 80.7 | 80.7 | 80.7 | 80.9 | 81.1 | 81.3 | 81.5 | 81.9 | 81.9 | 81.9 | 82.1 | 82.8 | 83.5 | 84.2 | 85 | 85 | 85 | 85.5 | 85.7 | 85.9 | 86.1 | 86.3 | 86.3 | 86.3 | 86.7 | 88.1 | 89.2 | 89.5 | 89.6 | 89.6 | 89.6 | 89.7 | 90.3 | 90.4 | 90.7 | 91.5 | 91.5 | 91.5 | 91.8 | 92.1 | 92.4 | 92.5 | 92.6 | 92.6 | 92.6 | 92.9 | 93.1 | 93.3 | 93.3 | 93.3 | 93.3 | 93.3 | 94.4 | 94.8 | 95.3 | 95.4 | 95.5 | 95.5 | 95.5 | 95.9 | 96.2 | 96.5 | 96.5 | 96.5 | 96.5 | 96.5 | 96.6 | 96.9 | 97 | 97.5 | 98 | 98 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
| Planning |  |  | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 8 | 9 | 12 | 12 | 12 | 15 | 18 | 21 | 24 | 27 | 27 | 27 | 30 | 33 | 36 | 39 | 42 | 42 | 42 | 43 | 44 | 45 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 59 | 60 | 61 | 61 | 61 | 61 | 61 | 62 | 63 | 64 | 64 | 64 | 64 | 64 | 66 | 68 | 69 | 70 | 71 | 71 | 71 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 73 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 80 | 81 | 82 | 83 | 84 | 84 | 84 | 86 | 88 | 89 | 89 | 89 | 89 | 89 | 89 | 90 | 90 | 90 | 90 | 90 | 90 | 91 | 91 | 91 | 92 | 92 | 92 | 92 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 97 | 97 | 97 | 97 | 97 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Gap |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 3 | 5 | 5 | 5 | 5.5 | 6 | 5 | 6.5 | 7.5 | 7.5 | 7.5 | 7 | 7.5 | 8.5 | 10 | 11.5 | 11.5 | 11.5 | 10 | 9.5 | 9 | 8.5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9.5 | 9.5 | 10 | 11 | 11 | 11 | 11 | 11 | 11.5 | 12 | 12.5 | 12.5 | 12.5 | 13 | 12.5 | 12 | 11.5 | 11 | 11 | 11 | 11.5 | 10 | 8.8 | 6.6 | 5.4 | 5.4 | 5.4 | 4.4 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 3.8 | 3.3 | 3.1 | 2.9 | 2.9 | 2.9 | 2.7 | 2.5 | 2.2 | 2.1 | 2 | 2 | 2 | 1.9 | 1.8 | 1.2 | 0.6 | 2.5 | 2.5 | 2.5 | 2.4 | 1.8 | 1.2 | 1 | -0.1 | -0.1 | -0.1 | 0.8 | 1.6 | 1.5 | 2.4 | 3.3 | 3.3 | 3.3 | 5.1 | 6.9 | 7.7 | 7.5 | 7.1 | 7.1 | 7.1 | 6.9 | 7.2 | 6.5 | 5.8 | 5 | 5 | 5 | 5.5 | 5.3 | 5.1 | 5.9 | 5.7 | 5.7 | 5.7 | 6.3 | 4.9 | 3.8 | 3.5 | 3.4 | 3.4 | 3.4 | 3.3 | 2.7 | 3.6 | 3.3 | 2.5 | 2.5 | 2.5 | 2.2 | 1.9 | 2.6 | 2.5 | 2.4 | 2.4 | 2.4 | 2.1 | 1.9 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | 1.6 | 1.2 | 1.7 | 1.6 | 1.5 | 1.5 | 1.5 | 2.1 | 1.8 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.4 | 1.1 | 1 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | 0.6 | Maret 1: 2.8
1.5
0.8
5

## Sheet1
1

## Timeline
No | Keterangan | Total Plan | Plan Now | Real | Maret |  |  |  | April |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | Agust
[5 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
1 | Project Preparation | 1 | 1 | 1
| Kick Off | 1 | 1 | 1
2 | Requirement Preparation | 29 | 15 | 7.3
| Gap Analysis | 6 | 28 | 3.5
| Blue Print | 6 | 2 | 1.9
| Mockup | 17 | 26 | 1.9
3 | Enhanchement | 49 | 56 | 0
| Environment Preparation | 1 | 1 | 0
| Development | 45 | 45 | 0
| Unit Testing | 3 | 3 | 0
4 | Acceptance | 16 | 2 | 0
| SIT | 3 | 3 | 0
| UAT | 10 | 2 | 0
| EUT | 3 | 7 | 0
5 | Support | 5 | 2 | 0
| Support | 5 | 5 | 0
Total |  | 100 | #REF! | #REF!
[13 empty] | Data | 1.7
| 0 | [5 empty] | Cuti Bersama Lebaran |  |  | May W9: upload; May W10: 1.6
Migration
[7 empty] | Transport to Production |  |  | May W10: 3.3
[7 empty] | Activity Done |  |  | May W10: 1.2
Activity In Progress
Planning
Go Live

## Copy of Timeline
No | Keterangan | Total Plan | Plan Now | Real | Maret |  |  |  | April |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | Septem |  |  |  | Oktober
[5 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33
1 | Requirement & Preparation | 30 | 30 | #REF!
| Kick Off & Project Charter | 5 | 5 | #REF!
| Gap Analysis | 10 | 10 | #REF!
| Blueprint | 15 | 15 | #REF!
2 | Enhancement | 33 | 33 | #REF!
| Environment Preparation | 2 | 2 | #REF!
| Development | 26 | 26 | #REF!
| Unit Testing | 5 | 5 | #REF!
3 | Acceptance | 20 | 20 | #REF!
| SIT Order Management | 3 | 3 | 3
| SIT Penagihan Royalty | 2 | 2 | 2
| UAT Order Management | 8 | 8 | 8
| UAT Penagihan Royalty | 2 | 2 | 2
| EUT Order Management | 3 | 3 | 3
| EUT Penagihan Royalty | 2 | 2 | 2
4 | Live Preparation | 15 | 15 | 15
| Data Preparation | 8 | 8 | 8
| Upload Migration to Production | 5 | 5 | 5
| Transport ke Production | 2 | 2 | 2
5 | Go Live | 1 | 1 | 1
6 | Support | 1 | 0 | #REF!
| Support | 1 | 0 | #REF!
Total |  | 100 | 99 | #REF!
|  |  | 0 | [6 empty] | May W9: Data; May W10: 1.7
| 0 | [5 empty] | Cuti Bersama Lebaran |  |  | May W9: upload; May W10: 1.6
Migration
[7 empty] | Transport to Production |  |  | May W10: 3.3
[7 empty] | Activity Done |  |  | May W10: 1.2
Activity In Progress
Planning | bar: August W24
Go Live

## Kurva S
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
Planning | 9 | 24 | 39 | 32 | 33 |  | 56 | 62 | 66 | 76 | 76 | 76 | 76 | 84 | 89 | 90 | #REF! | #REF! | 93 | 94 | 96 | 97 | 98 | 98 | 99
Realisasi | 6.5 | 14 | 31 | #REF! | 38 |  | 50.7 | 56.5 | 60.5 | 68.3 | 72.7 | 72.7 | 73.2 | 79.7 | 82 | 83 | #REF! | #REF! | 89.7 | 90.9 | 93.2 | 95.5 | 96.5 | 97 | 99
Gap | 2.5 | 10 | 8 | #REF! | -5 |  | 5.3 | 5.5 | 5.5 | 7.7 | 3.3 | 3.3 | 2.8 | 4.3 | 7 | 7 | #REF! | #REF! | 3.3 | 3.1 | 2.8 | 1.5 | 1.5 | 1 | 0

## Copy of Kurva S
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
Planning | 9 | 24 | 39 | 32 | 33 |  | 56 | 62 | 66 | 76 | 76 | 76 | 76 | 84 | 89 | 90 | #REF! | #REF! | 93 | 94 | 95
Realisasi | 6.5 | 14 | 31 | #REF! | 38 |  | 50.7 | 56.5 | 60.5 | 68.3 | 72.7 | 72.7 | 73.2 | 79.7 | 82 | 83 | #REF! | #REF! | 89.7 | 90.9 | 92.3
Gap | 2.5 | 10 | 8 | #REF! | -5 |  | 5.3 | 5.5 | 5.5 | 7.7 | 3.3 | 3.3 | 2.8 | 4.3 | 7 | 7 | #REF! | #REF! | 3.3 | 3.1 | 2.7
muter2 da wkkw

## Master Data
Master Data | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Master Material & Kode Material | bar: 5
Material vs Plant | bar: 5
Semen Zak vs Kantong | bar: 5
Material MD
Brand vs Semen Zak
Brand vs Plant vs Royalty
Demand Marketing
Target Distribution
Mapping Ship To
Sourcing Plant
Pricing Semen
Semen Zak vs Kantong vs Distrik
BOM
Routing PP
Production Version
Cost Estimate
Material vs Conveyor
Ongkos Angkut
Jatah Expediture